## Sprint 4
Issue # | User story | Associated Tasks | Story points associated (1, 2, 3, 5, 8,) | Priority | Risk | Risk Explanation | Responsible | Due date
99 | All user stories will be tested to ensure application functionality | - Create unit tests for all features and edge cases - Create acceptance tests for all user stories from all sprints | 5 | MEDIUM | LOW | We already have previously made unit and acceptance tests, so we just need to follow what we did before. There's also no new features in this sprint, so we're just testing improvements to existing components. | - Juan - Joseph | 2026-04-14
100 | The project files and code structure will follow best practices | - Organize project files and folders to follow guidelines in appendix - Approve a static analysis tool with the TA - Repair 5 code bugs found by a static analysis tool | 5 | HIGH | HIGH | Code refactoring could potentially lead to bugs in related components of the site. Since not everyone understands the inner workings of all components, thorough testing will be important to ensure there are no side effects. | All team | 2026-04-14
101 | The sprint planning and development will be well documented | - Create sprint plan - Add sprint logs - Create meeting minutes - Create github issues with proper relations | 2 | HIGH | MEDIUM | This sprint involves many changes to existing components, so if two people are working on related parts, there is a risk of undoing work or mismatching designs due to miscommunication. The plan needs to clearly seperate work and specify the desired result, considering all other tasks. | All team | 2026-04-14
110 | The visual design of previous sprint features will be unified | - Fix routing issues in the navbar - Make the navbar transparent with a profile icon - Improve colours and structure of profile page to match the homepage - Display all website features on the homepage | 8 | HIGH | MEDIUM | There are many redesigns and components being moved around, so there is a risk of design mismatches or unintended bugs in other areas of the site. | - Anais - Berny | 2026-04-14
102 | The recipe management flow will be intutivive and visually responsive | - Make any ingredient name usable without using a pre-set list - Fix the loading of images in recipe panels - Make recipe management accessible from the home page | 5 | MEDIUM | LOW | This story mostly involves fixing issues from preovious sprints. None of the logic is too complicated. | - Joseph - Berny - Anais | 2026-04-14
103 | The user will be able to view their past and future recipe plans | - Make multi-month navaigation for recipe planner - Make previous and future 3 months viewable and usable - Add the snacks category to calendar days | 3 | LOW | LOW | We just need to expand the functionality that has already been put in place. This component is also fairly isolated so there shouldn't be many edge cases | - Berny - Ashton - Zain | 2026-04-14

## Sprint 3
Issue # | User story | Associated Tasks | Story points associated (1, 2, 3, 5, 8,) | Priority | Risk | Risk Explanation | Responsible | Due date
69 | The user will be able to view modify a weekly calendar of recipes | - Create a calendar view page - Implement adding, editing, and removing recipes from calendar days - Prevent the same recipe from being added more than once per week - Implement a button to add AI generated recipe and to the calendar | 8 | High | High | This story involves complex logic to implement a calendar that is accurate to the current date and each date can hold recipe data. The AI recipe generation also needs to be properly integrated with the recipe management system. | - Joseph - Ashton - Zain - Berny | 2026-03-27
31 | The user will be able to enter a recipe selection tournament to help them choose out of their options | - Added AI recipe card creation using Google Gemini - ensured that tournament would only start when a recipe is present - (Bug) in light mode the text under the tournament was unreadable, a fix was implemented to resolve this - (Bug) the routing in the card was wrong and didnt handle null values. - (Bug) certain text in recipe was also unreadable when in dark mode on tournament page. - Show full details of recipe instead of just a summary. | 8 | High | High | This story was high risk as it required complex routing between pages and the implementation of AI was tricky. Risk of prompt injection can cause arbitrary code to run. meaning a risk of API key leaks. Also google being down for whatever reason can cause major issues. Mishandling API key was also a risk that needed to be handled. | - Ashton - Juan -Joseph - Anais | 2026-03-27
71 | The sprint planning and development will be well documented | - Create sprint plan - Add sprint logs - Create acceptance tests for sprint 2 - Create meeting minutes - Create unit tests for sprint 1-2 | 2 | Low | Low | No new functionalities are being introduced. Plan is flexible to change. | - Joseph - Anais - Ashton - Berny - Juan | 2026-03-27

## Sprint 2
Issue # | User story | Associated Tasks | Story points associated (1, 2, 3, 5, 8,) | Priority | Risk | Risk Explanation | Responsible | Due date
3 | The user will be able to manage their diet preferences and allergies in their profile page | - Implement saving preferences to database | 2 | HIGH | MEDIUM | Part of this user story was finished in sprint 1, but a bug related to the backend would affect many other tasks in sprint 2. Specifically the recipe management page. | - Berny | 2026-02-27
31 | The user will be able to manage a list of recipes | - Create UI for recipe management page - Implement functionality for creating, editing, deleting that syncs with backend - Create a search bar for recipes - Create a filter for different recipe attributes | 5 | HIGH | HIGH | This feature depends on functionality being consistent between the frontend and backend, which can cause difficult to identify bugs, especially with images and different data types being passed over the api. | - Joseph - Anais - Berny - Ashton - Juan | 2026-02-27
30 | The user will be directed to a homepage after logging in | - Create homepage UI - Implement navbar with functional routing - Add a logout button | 3 | LOW | LOW | Does not require many functional components, and can be easily joined with existing components. | - Zain - Ashton | 2026-02-27
35 | The sprint planning and development will be well documented | - Create a sprint plan - Create tasks on github - Log development hours - Track meeting minutes - Close stale branches on repository | 2 | MEDIUM | LOW | No new functionalities are being introduced. Plan is flexible to change. | All team members | 2026-02-27
25 | The project should run automated tests for each change pushed to the repository to catch critical errors early. | - Setup the initial acceptance tests - API endpoints tests - Frontend user management tests - CI/CD set up of Dev branch and limiting to PR in DEV and MAIN with new test | 5 | HIGH | HIGH | This feature is what allows the program to catch errors early. Catching errors early is what allows the system to be as cost and time efficient as possible. CI/CD pipelines ensure that an added functionality does not break the program. | - Juan | 2026-02-27

## Story points chart
Sprint | Planned story points | Completed story points | Total planned story points | Total completed story points | Notes
1 | 13 | 11 | 13 | 11 | Preferences was unfinished
2 | 15 | 17 | 28 | 28 | accounts for unfinished sprint 1 stuff
3 | 18 | 13 | 46 | 41 | Weekly calendar missing snacks, Ai generation buggy
4 | 28 | 26 | 74 | 67 | Not all tests done