## Sprint 2
Issue # | User story | Associated Tasks | Story points associated (1, 2, 3, 5, 8,) | Priority | Risk | Risk Explanation | Responsible | Due date
3 | The user will be able to manage their diet preferences and allergies in their profile page | - Implement saving preferences to database | 2 | HIGH | MEDIUM | Part of this user story was finished in sprint 1, but a bug related to the backend would affect many other tasks in sprint 2. Specifically the recipe management page. | - Berny | 2026-02-27
31 | The user will be able to manage a list of recipes | - Create UI for recipe management page - Implement functionality for creating, editing, deleting that syncs with backend - Create a search bar for recipes - Create a filter for different recipe attributes | 5 | HIGH | HIGH | This feature depends on functionality being consistent between the frontend and backend, which can cause difficult to identify bugs, especially with images and different data types being passed over the api. | - Joseph - Anais - Berny - Ashton - Juan | 2026-02-27
30 | The user will be directed to a homepage after logging in | - Create homepage UI - Implement navbar with functional routing - Add a logout button | 3 | LOW | LOW | Does not require many functional components, and can be easily joined with existing components. | - Zain - Ashton | 2026-02-27
35 | The sprint planning and development will be well documented | - Create a sprint plan - Create tasks on github - Log development hours - Track meeting minutes - Close stale branches on repository | 2 | MEDIUM | LOW | No new functionalities are being introduced. Plan is flexible to change. | All team members | 2026-02-27
25 | The project should run automated tests for each change pushed to the repository to catch critical errors early. | - Setup the initial acceptance tests - API endpoints tests - Frontend user management tests - CI/CD set up of Dev branch and limiting to PR in DEV and MAIN with new test | 5 | HIGH | HIGH | This feature is what allows the program to catch errors early. Catching errors early is what allows the system to be as cost and time efficient as possible. CI/CD pipelines ensure that an added functionality does not break the program. | - Juan | 2026-02-27